## Introduction
This is the Project Tracker
You will use this to track your work on your project. The first step is to identify your team on the Team sheet. Also on the Team Sheet, you will specify the address of your GitHub repository for the project. After that, you will complete the Features sheet, which is a summarized version of the use cases you wrote for the last assignment. In addition to listing summary versions of your use cases, recall that you also listed in your Business Requirements document various resources users will need to use your product, so include as "features" the task of creating such resources so you can allocate time to making them.
Then you will identify, in helpful detail, the tasks you will perform to implement each feature. You have to be detailed here, thinking very clearly about what it will take to pursue each task in terms of time.
AFter that, on the Test Plans sheet, you will describe how you will test that each feature is working. Finally, on the Work Log tab, you will enter entries for each work session you spend building your project. Include links to particular assets in your GitHub respository that I can refer to to see evidence of your work.
The purpose of this sheet is to serve as a guide and a tracking mechanism as you try to build the various features of your project.

## Team
Team Members
Team member name | Email address
Carter Schenke | carterschenke@lewisu.edu
Project GitHub | https://github.com/CarterS01/TrailFinder
Just list the names and email addresses of the members that comprise this team. If there is only one person, just specify one name and email address.

## Features
Feature List
Feature ID | Feature Name | Feature Description
SRCH | Searching for a trail | On the main screen, the user will select the “Find A Trail” button. This will open a new screen. At the top will be a field to enter a zip code or city, and underneath that, a dropdown menu where the user can select a radius from that zip code or city to search in. Directly underneath that will be checkboxes where the user can choose a difficulty between green, blue, black, double black, or any combination of the four to be shown in the search results. Underneath that will be two dropdown menus for features that the user can select. First, the user will choose between “Trail Terrain”, with technical and smooth as the options. Next, the user will choose “Trail Type”, with uphill, downhill, and mixed as the options. Both menus will have “no preference” as an option as well. Next will be a series of checkboxes labeled “jumps”, “berms”, “drops”, “rock rolls”, and “skinnies”. These are various features that can be found on mountain biking trails. The user will select the check box next to the name of the features they want included in the trails in the search results. The user will then select the “Show Trails” button, and a list of trails nearby will be shown to them, ordered by how much they match a user’s preference. This will be done by calculating the percentage of the user’s preferences that are met by that trail. Trails with a 70% or higher match will be shown. If no trails are found that match with at least 70%, a message will appear saying such, with two buttons, one going back to the main menu, and the other to show a list of all trails in the area, ordered by the percentage in which they match the user’s preference.
RECS | Trail recommendations | Beneath the “Find A Trail” button will be a button that says “Recommend A Trail”. The user will press this button, and will be prompted for their location, either by zip code or city. After entering this, a list of trails in the area will be given, ordered by how closely they match the user’s typical preference, which will be determined by which option the user selects most often in the Searching For a Trail feature. If the user’s preferences are inconsistent, or the user has not searched enough trails to indicate a preference, then the list will instead be ordered by popularity of trails.
NOTE | Adding trail notes | When viewing a list of trails, such as in the previous two steps, a user may click on the trail, which will show a more detailed description of the trail, as well as an “Add Notes” button. Clicking on this button will open a text panel, where they can write a note up to 500 characters about the trail to see any time they view the trail in the future. After writing the note, the user may press the “Save” button to save it and return to the trail’s details page, or the “Cancel” button to return to the page without saving the note.
SAVE | Saving trails | On the trail’s details page, there will be an outline of a bookmark icon next to the trail name. Selecting this will fill in the icon and save the trail for the user. Selecting it again will unsave the trail and revert the icon back to the unfilled version. At the main menu, the user can select the “Saved Trails” button and view the trails they have saved on a new page. At the top of this page will be a “Sort & Filter” button. Selecting it will bring up a menu with the following filter options: “Distance”, which will allow the user to enter a location (city or zip code) and filter their saved trails by a radius from that location, “Difficulty”, which will allow the user to choose to only show saved trails of certain difficulties using a list of the difficulties (as described in the first feature) with check boxes next to them, and the following sorting options: “Difficulty”, which sorts by the difficulty, either ascending or descending, and “Nearest”, which sorts the trails by how close they are to the user’s location. Note that the filters will not automatically sort the list, but instead the sorting options can be used to sort the filter results in any way the user desires.
Here we list the specific features of your final project. This is just an alternative way to express what you did for the last assignment. Features are the things your project offers the user, so focus on what the user will experience. What will the user be able to do? How will they interact with what you are building? What will they see when they use what you are building?
For each feature, specify a Feature ID. Perhaps this is just a number, or maybe its a short abbreviation that you'll use to uniquely identify each feature. Then specify a name for the feature that describes cleaerly what it concerns. Finally, offer a very specific but brief description. You already did this in the preceding assignment, but if you weren't specific there, you need to be specific here. Otherwise, you can copy the use case text you wrote in that last assignment. The description you provide here should give us a clear understanding of what the user will be able to do and see and interact with in your product.

## Task Estimation
Task Estimation
Feature ID | Task ID | Task Name | Task Description | Estimated Hours | ID of tasks this depends on | Assigned team members
SRCH | SRCH.01 | SQL Database | An SQL database needs to be created to hold the data for each trail. | 4 |  | Carter
SRCH | SRCH.02 | Main Page Frontend | The frontend for the main page needs to be created, this will consist of three buttons, one for this feature labeled “Find A Trail”, one for feature RECS that says “Recommend A Trail”, and one for feature SAVE that says “Saves Trails”. | 2 |  | Carter
SRCH | SRCH.03 | Main Page Backend | Backend functionality needs to be given to the main page, this will simply make it so the first button in task SRCH.02 leads to the page in task SRCH.04, and the second button leads to the page in RECS.02. | 1 | SRCH.02 | Carter
SRCH | SRCH.04 | Find a Trail Frontend | The frontend /design for the Find a Trail page needs to be created, with the possible trail attributes listed and the proper dropdown boxes and checkboxes displayed. | 2 |  | Carter
SRCH | SRCH.05 | Find a Tail Backend | The functionality for the Find a Trail feature needs to be created. It needs to take the user’s inputs, compare them with the trails in the SQL database, and then make a list of trails that match at least 70% of the desired features, ordered by the percentage in which they match. | 10 | SRCH.01, SRCH.04 | Carter
SRCH | SRCH.06 | Find a Trail Results Page | A page that displays the results of Find a Trail in an easy-to-read format for the user must be created using the results of task SRCH.05. | 4 | SRCH.04, SRCH.05 | Carter
SRCH | SRCH.07 | Create User Profile Functionality | Create a user profile capable of storing things only visible to them, such as notes. This can be accomplished using a CSV file/SQL database linked to a specific account, and a server-side encrypted file for storing user passwords. | 8 |  | Carter
SRCH | SRCH.08 | Store User Preferences | A CSV file will be created with all possible trail features, with an associated count that starts at 0. Each time a user uses feature SRCH, the count will go up for each feature selected by the user. This will be used later for feature RECS. | 4 | SRCH.05 | Carter
RECS | RECS.01 | Read CSV File | Upon the press of the second button in SRCH.03, the CSV file should be read, and opposed features (features where a user must select one or the other) will be compared, and the one with the higher count will be chosen for the recommendation search. | 2 | SRCH.02, SRCH.08 | Carter
RECS | RECS.02 | Recommendation Page Backend | This step will be nearly identical to SRCH.05, but using the data taken from RECS.01 rather than the user’s inputted data. | 1 | SRCH.01, RECS.01 | Carter
RECS | RECS.03 | Recommendation Results Page | Once again, this will be nearly identical to a previous task, SRCH.06, but this time using the results from RECS.02. | 1 | RECS.02 | Carter
NOTE | NOTE.01 | Add Notes Section | Add a section in the pages from SRCH.06 and RECS.03 where a user can add notes to the trails displayed. Additionally, add buttons for saving the notes and cancelling the entry. | 3 | SRCH.06, RECS.03 | Carter
NOTE | NOTE.02 | Add Notes Functionality | Allow text to be typed into the notes section. Make the cancel button exit text entry without saving it. Make the save button store the notes in the SQL database for that trail, only for that specific user. | 4 | SRCH.01, NOTE.01 | Carter
SAVE | SAVE.01 | Add Save Button | Add an outline of a bookmark button to the pages from SRCH.06 and RECS.03 that toggles between the outline and filled in when clicked. | 4 | SRCH.06, RECS.03 | Carter
SAVE | SAVE.02 | Save Button Functionality | Make the bookmark button create an entry in an SQL database to store a link to the trail in a user’s profile when pressed, and delete that entry when pressed again. | 5 | SRCH.01, SAVE.01 | Carter
SAVE | SAVE.03 | Saved Trails Page Frontend | Add a page that displays the saved trails to the user, or a message saying “No Trails Saved” if the user has no saved trails. Also, add the filter button with the filter options described in the SAVE feature. | 5 |  | Carter
SAVE | SAVE.04 | Saved Trails Page Backend | Have the saved trails page look in the SQL database for which trails to display, and add functionality to the filter options that will sort the displayed trails, if there are more than 1. | 8 | SRCH.01, SAVE.02 | Carter
Here we list the tasks you estimate will be needed to complete your project (in other words, to implement its features). Each row represents a task.
For each task, specify the ID of the corresponding feature. These should come from the list of features you provided on the Features sheet, so perhaps use an Excel formula to set them. Then specify the ID of this task. Perhaps it's just a number, or maybe it's an abbreviation, or maybe it's a combination of the feature ID and a number or a letter - for example, if the feature ID is 1 and you want to represent that this is the first task for implementing feature 1, perhaps you could set the Task ID as 1.1 or 1.A.
Next, specify a Task Name. It should clearly but briefly describe what this task concerns.
Next, describe clearly what is needed to accomplish this task. What steps will you take to carry it out
Then specify how many hours it will take to complete the task. This is just an estimate at this point. If this task depends on another task being done, indicate the task ID of the task it depends on in the next column. Finally, specify who is responsible for completing the task. This could be multiple team members if two or more people are needed to complete the task.
Make sure you in include in your time estimate for each task some time for testing that the task was done correctly / is producing the right output. A good rule of thumb is to allot an additional amount of about 20% to 25% of the time it took to do a task for testing that it works. You won't be testing every single task, and the test plans on the test plans sheet will connect to the overall features rather than the individual tasks. Nevertheless, if you follow the rule of thumb that 20% to 25% of your work effort should be added for testing, you will be sure to allow the right amount of time for it.

## Test Plans
Test plans
Feature ID | Test ID | Test Name | Test Description | Tester | Successful outcome
SRCH | 1.1 | Find a trail | Select the “Find A Trail” button and ensure it leads to the trail search page. From here, select various options before selecting the “Search” button, repeat multiple times selecting different features. By default, the features should have “No Preference” selected, therefore hitting “Search” without any input after first arriving on the trail search page should work as expected. For at least one test, choose features that will not match any trails with more than a 70% rate, a message saying “No trails that meet your criteria found” should appear. | Carter | The trail results page should be displayed.
SRCH | 1.2 | Login | Select the “Login” button. A prompt for a username and password should appear. Enter in an incorrect username with any password, confirm that the system does not allow a login and displays a message saying “Incorrect username or password.” Try again with a correct username and incorrect password and confirm that the same message appears. Try again with a correct username and password and confirm that you are brought back to the main page, this time with your username in place of the login button. | Carter | The main page will display with the username in place of the login button.
NOTE | 2.1 | Save notes | Once on the trail results page from test 1.1 displays, select the notes option. A text box should appear. Type in some text, select the “Cancel” button, and confirm that no note has been added. Select the text box again, type in some text, and select the “Save” button. Confirm text has been added. Return to the trail search page, choose a search that will display the trail the note was added to, search it, and confirm the note is still present. | Carter | A note will be displayed on a trail any time it is returned in a search.
SAVE | 3.1 | Save trails | After performing another trail search as described in test 1.1, select the bookmark icon next to a trail, and then again. The bookmark icon should not be filled it. Select the bookmark icon next to a second trail. The icon should remain filled in. Return to the homepage and select the “Saved Trails” option to verify that the second trail bookmarked shows on the saved trails page, but the first one that was unbookmarked does not. | Carter | The second trail bookmarked will display in the saved trails page, but not the first one.
RECS | 4.1 | Get recommendations | From the homepage, select the “Recommend A Trail” button. Enter in the area code of the search, select a distance range that would include some but not all trails entered into the database for testing, and select the “Recommend” button. Confirm that all trails that should show up for testing show up, and ones that shouldn’t do not. Then, go back to the recommendation page and attempt to search without entering an area code. The button should be grayed out and not function. | Carter | The recommended trails display properly.
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
On this sheet, describe how you will test each feature. Each row represents a test you will conduct. You might have multiple tests for each feature to confirm that that feature is working.
In the first column, specify the ID of the feature listed on the Features sheet that this test corresponds to.
In the Test ID column, give this test a unique id. Perhaps it is a combination of the feature ID and a number or letter or abbreviation for this particular test. For example, if the related feature is ID # 1, and this is the first test for ID #1, perhaps the test ID should be 1.1 or 1.A. But you can choose your own unique id system.
In the Test Name column, specify a clear, concise name for this test.
In the Test Description column, specify a clear, concise, but complete description of how the test will be conducted.
In the Tester column, indicate the names of the people on the team who will conduct the test.
Finally, in the Successful Outcome column, describe how you will know that your work passed this test. In other words, how will know that your work successfully implemented the feature it supports?

## Work Log
Task ID (from Task Estimation Sheet) | Date the work was done | Time spent (hours) | Work done by whom? | Description of what was done (be clear in describing the work you did. A step-by-step description would be good.) | Document on GitHub that provides more detail about what was accomplished through this task.
SRCH.02, SRCH.03, SRCH.04 | 2025-10-27 | 1 | Carter | A main Python file was created, as well as HTML files for each page. Functions to call each page were added to the Python file. The basic structure for the main page’s frontend was set up in it’s HTML file, with navigation to all other pages set up. The beginnings of the frontend for the Find A Trail page was added to it’s HTML document.
SRCH.01, SRCH.04 | 2025-10-28 | 1.5 | Carter | The database file was created, and three tables were created. The first storing trail information, the second storing user information, and the third storing user’s notes, identified by the user and trail IDs from the first two tables. The exact layout of this database will likely change, but this will work to begin creating functionality. The HTML file for the Find A Trail page was updated to include the necessary dropdown and check boxes, as well as a submit button that currently leads to a placeholder page.
SRCH.01, SRCH.02 | 2025-10-29 | 2 | Carter | A few samples trails were added to the trails table in the database for testing purposes. Additionally, a CSS file was created for the main page and for fonts, and further additions to the frontend of the page were made. These included adjustments for the layout, font, and color scheme.
SRCH.04 | 2025-10-30 | 1 | Carter | Frontend development was continued for the Find A Trails page. A CSS file was added and styling was applied for layout, spacing, font, and colors.
SRCH.02 | 2025-10-31 | 2 | Carter | A TrailFinder logo was created using GIMP to trace a royalty-free image of a mountain biker, and Pixlr to put it together with text, shapes, and color. About an hour was spent on trying to add it to the navbar (this is still a work in progress at the moment).
SRCH.07 | 2025-11-04 | 3 | Carter | Created frontend for login page using find.css to style it. This CSS file was renamed to forms.css and altered to apply to any submission form pages, currently just the Find A Trail and Login pages. Backend was started on the login page to accept username and passwords. Some test users were entered into the "users" table in data.db, and a file called sql.py was created to test hashing functions and ways to validate hashed passwords with the database in a simpler environment with less variables before implementing it into the webapp. Functions to hash user passwords and validate entered passwords were created.
SRCH.07 | 2025-11-05 | 2 | Carter | The test code from sql.py was added to the login function in main.py and adapted it to fit. I spent some time the code via comments for easier understanding in case anything needs to be changed later. The password field on the login page was changed to hide the user input and not display suggestions of previously entered passwords. A file called find.py was created for form functionality for the Find A Trail page, and find.tml was completely redone to use the flask_wtf library for forms. Because of this, forms.css also had to be modified to suit the new HTML in both find.html and login.html. Code was added to the find_a_trail function in main.py to store the user inputs from the Find A Trail page. An alternate way to run the app was added at the end of main.py for connecting with devices other than the host device, to test how the webpage displays on other devices and screen sizes.
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter
Carter